## Sheet1
The Guiding Principle |  | Time to Build Visitor Pre-Registration
Build the system so payments can arrive from three sources without changing anything else:
1. Manual entry by admin (what you'll use now)
2. CSV statement upload (the bridge — Co-op Bank gives you a statement daily)
3. API callback (the future — Co-op Bank API or aggregator)
Since all three sources write to the same payments table, the rest of the system (invoices, blocking, SMS) doesn't care where the data came from.
📅 What's Doable Now (No External Dependencies)
✅ Week 1 — Database & Seed Data
1. Run the T-SQL schema I gave you against Azure SQL.
2. Add a units table and populate it with all the houses in the estate (you'll need the list from the estate committee).
3. Link existing residents to their units.
4. Insert the billing_settings row (KSh 2,000, due day 5, etc.).
Deliverable: All residents have a unit_id and house_number.
✅ Week 2 — Invoice Generation (Admin-Triggered)
1. Backend endpoint: POST /api/admin/invoices/generate?month=2026-04
2. Loops through all occupied units, creates one invoice per unit for that month.
3. Skips if an invoice already exists for that unit+month.
Deliverable: Admin clicks a button, all invoices for the month are created.
Later, this becomes a cron job on the 1st of every month. Right now, manual trigger is fine.
✅ Week 3 — Manual Payment Entry (Admin UI)
This is your M-Pesa stand-in for now.
1. Backend: POST /api/admin/payments/manual — admin enters:
House number (or unit)
Amount
M-Pesa receipt code (optional)
Payment date
Notes
2. Backend: allocates the payment to the oldest unpaid invoice for that unit.
3. Backend: updates invoice.amount_paid and invoice.status.
4. Frontend: a simple form with a "Record payment" button.
Deliverable: Admin can record a payment in 10 seconds after seeing it on their phone's M-Pesa SMS.
✅ Week 4 — Admin Payments Dashboard
1. admin-payments.html — a queue showing:
Pending payments (manually entered or later from API)
Verified payments
Rejected payments
2. Verify / Reject buttons (mirror your existing provider verification pattern — reuse that code).
3. Filters by date, unit, status.
4. Total collected this month.
Deliverable: Admin has a full payment ledger.
✅ Week 5 — CSV Statement Upload (The Bridge)
This is the key trick that makes manual work bearable without API access.
1. Admin downloads the daily Co-op Bank statement (CSV or Excel).
2. Uploads it at /api/admin/payments/upload-statement.
3. Backend parses rows: date, amount, account_ref (house number), mpesa_receipt.
4. For each row, creates a pending payment record (skips duplicates by receipt number).
5. Auto-matches to units by house number.
6. Unmatched rows are flagged for admin review.
Deliverable: Admin uploads one file per day instead of typing 50 payments.
This is what you'll use until Co-op Bank API access is ready — and honestly, for a small estate, it may be all you ever need.
✅ Week 6 — Resident Billing Page
1. billing.html — resident sees:
Current month invoice
Balance (paid / unpaid)
Payment history
Paybill instructions (1024162, account = house number)
A "I have paid" button → creates a pending payment with resident-submitted M-Pesa receipt for admin to verify
2. Dashboard header card: "You are paid up" / "You have KSh X outstanding".
Deliverable: Residents can self-serve.
✅ Week 7 — Overdue Detection & Access Blocking
1. Backend job (run daily or on admin click): mark invoices as overdue past due date + grace.
2. Compute residents.access_blocked = true for units with any overdue invoice.
3. Admin can manually override the block.
4. Show a red badge on the admin residents list.
Deliverable: Access blocking logic is live (gate enforcement comes later).
✅ Week 8 — Visitor Pre-Registration (No SMS Yet)
1. Resident page visitors.html:
Add visitor (name, phone, ID, purpose, visit date)
Add vehicles (type, plate, driver)
For groups: add multiple visitors under one booking
Generate a 6-character access code
Valid for 48 hours from creation
2. Backend: POST /api/visitors, GET /api/visitors/mine.
3. Admin page admin-visitors.html:
List of pre-registered visitors by date
Approve / deny
Print-friendly view (reuse your existing PDF export pattern)
4. Verified providers on the platform get a shortcut: request an access code directly from their dashboard.
Deliverable: Full visitor pre-registration flow.
✅ Week 9 — Admin Dashboard Tiles + Reports
Add tiles to admin.html:
Pending payments
Overdue residents
Today's expected visitors
Visitors currently checked-in
Payments collected this month
Add reports:
Payments register (Excel/PDF — reuse existing export code)
Visitor register by date (Excel/PDF)
🔌 What We Defer to Later
These all require external accounts or APIs, so they wait:
Feature | Blocker
Real-time M-Pesa callback | Co-op Bank API access or Safaricom Paybill
SMS reminders / overdue alerts | Africa's Talking account
Gate check-in scan | Hardware + Phase 6
Automatic access blocking enforcement at gates | Phase 6
🏗️ The Order, Condensed
1. DB schema ← Start here, today
2. Unit list + resident linking ← Needs estate committee data
3. Invoice generation (manual trigger)
4. Manual payment entry (admin UI)
5. Payments dashboard (verify/reject queue)
6. CSV statement upload ← This replaces M-Pesa for now
7. Resident billing page
8. Overdue + blocking logic
9. Visitor pre-registration (resident + admin)
10. Reports & dashboard tiles
11. (Later) M-Pesa / SMS / Gate

## Sheet2
# | Module | Time | Notes
1 | Test check-in / check-out | 5 min | Endpoints are built but not clicked through end-to-end
2 | SMS via Africa's Talking | 1–2h | Sign up, add credentials, integrate — every email also sends SMS
3 | Capacitor mobile wrapper | 2–4h | Installable Android/iOS app from the existing frontend
4 | Polish | varies | HTML email templates, "resend code", bulk actions
5 | Housekeeping | 30 min | Update README, clean test data, tag a release
6 | Take a break | — | Rest; come back later
__

## Sheet3
🎯 What's Not Built Yet
Feature | Status
USSD menu | ❌ Not started
WhatsApp Business API | ❌ Not started
Two-Way SMS (shortcodes) | ❌ Not started
SMS to admin/security notifications | ❌ Not scoped
Capacitor mobile wrapper | ❌ Deferred
Production SMS Sender ID registration | ❌ Not applied
House-number seed for all residents | ⏳ Partially done
Cron for monthly invoice generation | ❌ Not automated
Visitor expiry cron | ⏳ Endpoint exists, no scheduler
🎯 My Honest Take
You've built a full-featured estate management portal with:
A complete billing system (with real payment reconciliation workflow)
A complete visitor pre-registration system (with 2-stage approval, dual-channel delivery, gate workflow)
Admin/security/resident dashboards
Real email + SMS integration
Proper audit trails
This is production-ready for a small-to-medium estate as soon as you:
1. Register a production Sender ID with Safaricom (~KES 8,700 + 2-5 days)
2. Top up Africa's Talking (~KES 500-1000/month for moderate use)
3. Finish assigning house numbers to all residents
The USSD, WhatsApp, and Capacitor work is expansion, not "fixing something broken."
🎯 Recommendation
Push now. Lock in the milestone:

## Sheet4
Three Common Welfare Models
Model A — Welfare Fund with Contributions
Residents contribute a fixed monthly amount (e.g., KSh 500) to a communal welfare fund. The fund pays out for pre-defined events.
Typical features:
Fixed monthly contribution amount
Every household on record as payer
Fund balance visible to all residents
Payout when a member experiences an event (death, illness, birth)
Admin approves payouts
Model B — Welfare Requests + Peer Donations
Residents post requests ("Help needed for X"), and other residents contribute individually (not through a fixed fund).
Typical features:
Resident creates a welfare request with description + target amount
Other residents pledge/contribute via M-Pesa
Progress bar showing how much has been raised
Admin verifies contributions
Request closes when target reached or expired
Model C — Both
A monthly contribution fund (Model A) + special case requests (Model B).
🎯 Typical Welfare Workflow (Model A)
text
1. Resident registers for welfare → agrees to KSh X/month
2. Monthly contributions tracked (same as billing)
3. Resident experiences qualifying event → submits request
4. Admin reviews request → approves or denies
5. Approved payout deducted from fund
6. All residents see ledger of fund balance + payouts
🎯 Questions Before I Design
I need six answers to build the right thing.
1 — Which model?
A — Fixed monthly contributions + fund payouts
B — Open requests + peer donations
C — Both
2 — Contribution amount
Fixed amount? (e.g., KSh 500/month) → admin-configurable like the KSh 2,000 billing
Or member-decided per request (Model B)?
3 — Who can request payouts?
Any registered resident
Only residents who've paid for N months
Any household, one request at a time
4 — Approval flow
Single admin approval
Two-stage like visitors (admin → committee)
Auto-approve if criteria met
5 — Fund accounting
Only contributions in
Contributions + external donations
Interest/adjustments manual by admin
6 — Visibility
All residents see full ledger (open book)
Only own contributions
Only totals visible, individual amounts private
🎯 Database Sketch (Model A — for context)
Once you pick a model, we'd add tables like:
Table | Purpose
welfare_members | Which residents opted into welfare
welfare_contributions | Monthly contributions per member
welfare_requests | Payout requests from residents
welfare_payouts | Approved payouts (deducted from fund)
welfare_ledger | Full audit: contrib + payout + balance
welfare_settings | Monthly amount, event types, rules
Then a welfare.html page for residents and a admin-welfare.html page for admins.
🎯 What I'd Recommend
Given how you've structured the estate (billing per household, admin approval workflow), Model C fits best:
Monthly contribution (like your KSh 2,000 billing — same invoice pattern)
Open requests for special cases (large funeral, medical emergency)
Two-stage approval for payouts (admin → committee, or admin → security lead)
Open ledger so everyone trusts the fund
📋 Just Reply With
text
1. Model: A / B / C
2. Amount: <number> (or "member-decided")
3. Request eligibility: any resident / N months paid / other
4. Approval: single admin / two-stage / auto
5. Fund sources: contributions only / + donations / + other
6. Visibility: full ledger / private / totals only
Example:
text
1. C
2. 500
3. any registered resident
4. two-stage
5. contributions only
6. full ledger
Once I have those six, I'll design the schema and ship the welfare module the same way we did billing and visitors — DB → routes → admin page → resident page.
What's your setup? 🚀